## Sheet1
Project Plan. Unit 2 - Cida (Tell me A Story)
| 4 Lessons a Week |  | Lessons Last 50 Minutes each |  | Project Deadline : 21st July 2008
Task Number | Task | SubTasks | Time Needed | Starting Date | Ending Date | Where to Save? | Contingency Time | Additional Notes | Done
1 | Preparation | Create a StoryBook folder | 5 Minutes | 2008-04-30 | 2008-04-30 | My UserSpace | None | - | *
|  | Choose a TestBuddy | 5 Minutes | 2008-04-30 | 2008-05-01 | - | None | James Swift Is the Test Buddy I chose, the same one from the previous project. | *
Update my Project Plan and Log
2 | Planning | Produce a Detailed Project Plan using the Planning Notes as assistance | 1 Lesson | 2008-05-07 | 2008-05-07 | Eportfolio | None | Save each Project Plan, as it is updated. | *
|  | Check the Plan with Mr Wood, to ensure that I am on the right path. | 1 Minute | 2008-05-07 | 2008-05-07 | - | None | Mr Woods, My Cida teacher approved my Project Plan. | *
Update my Project Plan and Log
3 | Keeping Track | Create a Project Log | On Going | 2008-05-07 | End Of Project | Eportfolio | None | What went well What went wrong and what effect it had Changes to the plan What happens next How you took account of feedback What happened at interim checkpoints How you made use of contingency time | *
Update my Project Plan and Log
4 | StoryBook Overview | Ideas – Think about: What will the story be. How is it told? Who is the audience? What is the purpose of the storybook? Use this as a guide, or a summary. | 1 Lesson | 2008-05-05 | 2008-05-08 | Additional Folder | None | • Be a complete story with a beginning, middle and end • Include a variety of multimedia assets which are embedded on the pages • Include some form of narrative • Include two routes and two different animated endings. • It is important that the audience is in control. The storybook must allow them to: • decide when to move on • move forward or back one page from any page • go to the contents page from any page • choose which route to take through the story. | *
Update my Project Plan and Log
5 | Gathering Assets | Create an Assets Table to record all assets used during the project. | 5 Minutes | 2008-05-08 | 2008-05-08 | Eportfolio. Assets folder for the assets used. | None | Use the example to plan layout. Only record the first four columns, giving location. Of each asset found. Only complete the other columns, if the asset is used. | *
Update my Project Plan and Log
6 | Proposal | Get some potential ides about the book, using the websites provided and others found. | 1 Lesson | 2008-05-08 | 2008-05-08 | Eportfolio | None |  | *
|  | Create the Proposal, using the layout to complete it. | 1 Lesson | 2008-05-12 | 2008-05-12 | Eportfolio | None | Target audience- Is it an individual or a group? Is it someone you know? Is it for a particular age group? Boys and/or girls? Reading age? Topic and style- What will your story be about? Is it just for fun or do you want users to learn something? What style do you want - fun, adventure, serious, etc? Characters- Who or what will be in your story? Are they people, animals or imaginary creatures? Are they goodies or baddies? Will they be real or cartoon? Outline of the story- How will your story start? What will happen next? Where will the action take place? Where and how will you offer the user a choice of routes? How will it end? Animated endings- What type of animation will you use? What will each animation do? | *
|  | Get Sir to approve my Proposal, I need this to move on. | 1 Minute | 2008-05-12 | 2008-05-12 | Project Log | None |  | *
Update my Project Plan and Log
7 | Detailed Designed | Write the script for the storybook. | 4 Lessons | 2008-05-14 | 2008-05-19 | Eportfolio | None | It must tell the story and describe what is happening at each stage - dialogue, what the characters are doing, etc. Without this you cannot plan your storyboards. | *
|  | Deciding what will happen on each page, this means splitting the story up into reasonable chunks, one for each page. Including the different routes that can be taken. | 20 Minutes | 1900-05-21 | 1900-05-21 | Eportfolio | None |  | *
|  | Produce a simple flow chart, which will show the direction of each animation, showing links and pathways. | 20 Minutes | 1900-05-21 | 1900-05-21 | Eportfolio | None |  | *
|  | Develop a set of detailed story boards, one for each page. Each storyboard will be detailed to show what the audience will see and experience. Either digitally, or hand drawn then scanned in. | 4 Lessons | 2008-05-21 | 2008-06-04 | Eportfolio |  | Each Story board should include: • the part of the story this page tells • background/scenery and layout • navigation features and links • font colours, styles and sizes • description of assets needed such as images, sound effects, narration, music, video, animation ect. Annotating designs, helps others to understand your choices.
| Time for Test Users and Reviewers | Make use of Feedback, including members of the target audience. | 30 Minutes | 2008-06-04 | 2008-06-04 | Project Log
Update my Project Plan and Log
8 | The Pages | Story Pages.-Use the detailed designs to help you create the pages. Make sure that you have all the assets you need, using your detailed designs to help you. Create each page using your detailed designs to help you. | 4 Lessons | 2008-06-04 | 2008-06-09 | Storybook |  | Test each page to make sure it is fit for audience and purpose. Make use of feedback from test users, including members of the target audience if possible. Check the complete set of pages: • are they consistent? • do they tell the story in an effective way? • is the decision point clear? • do the different routes through the story make sense? All action will take place on the page, making sure all buttons, links and pathways are embedded and do not open up on different pages.
|  | On the contents page there must be links to key points within the storybook. The number of links in your contents page will depend on how your story is structured - whether you have chapters, scenes, or just page numbers, etc. Design your contents page using a storyboard. Annotate it to explain your design decisions. It must: • include links to key points within the storybook • use a suitable image for each link. | 2 Lessons | 2008-06-11 | 2008-06-11 | Save the StoryBoard in the Eportfolio, Save the Contents Page in my StoryBook folder. |  | Test it to make sure that it is fit for audience and purpose, making use of feedback from users.
|  | The Cover- Design and create a storybook cover, it should be attractive and eye catching, and should make the target want to read the story | 1 Lesson | 2008-06-12 | 2008-06-12 | StoryBook |  | Test it to make sure that it is fit for audience and purpose, making use of feedback from users.
|  | Check that each page is suitable, that every page fits together, pictures link, pages can be seen to have similariites. | 1 Lesson | 2008-06-16 | 2008-06-16 | Project Log
Update my Project Plan and Log
9 | Animated Finale | Use a timeline storyboard to design each animated finale. | 4 Lessons | 2008-06-18 | 2008-06-23 | Eportfolio |  | Each ending must: Run for at least 20 seconds Include an original soundtrack you have produced - this doesn't have to be music but it must be original! Run automatically without user input.
The animations do not have to be two completely different ones, but can be different versions of each other. Use the timeline Story board to help create each animated finale. Get feedback from different users to ensure that each animated finale is appropriate. Make sure I have all the assets and then start creating the pages.
|  | Each route through the story must end with an animated finale. That leaves a lasting impression. Each ending must be a "Full" animation, not just moving images. |  |  |  | Storybook |  | Test the animations to make sure they are fit for audience and purpose. Make use of feedback from test users, including members of the target audience if possible
Update my Project Plan and Log
10 | Building It | Make sure all the components are in the stroybook folder, to help put the storybook together. | 5 Minutes | 2008-06-25 | 2008-06-25 | Completed StoryBook in the StoryBook folder.
|  | Build the storybook using the designs as assistance. | 2 Lessons | 2008-06-25 | 2008-06-26
|  | Test your storybook to make sure it works correctly. Some of the questions you need to answer are included in this testing sheet. | 1 Lesson | 2008-06-30 | 2008-06-30 |  |  | Use the testing sheet to help make sure it works correctly, Some of the questions that are needed answered are in the Testing Sheet.
| Time for Test Users and Reviewers | Make use of Feedback from test users and members of the target audience, use the feedbakc sheet to help create questions. | 30 Minutes | 2008-07-02 | 2008-07-02 |  |  | Make any necessary changes to the form.
Update my Project Plan and Log
11 | Eportfolio | The StoryBook should be displayed in the Eportfolio, along with supporting evidence. | - | - | - | - |  | Work on it, as I work along the project. Make sure that the final storybook is clearly presented in one section with a link to the cover page
|  | Make a detailed list of everything that needs to be in the plan, using the checklist to help. | 20 Minutes | 2008-07-02 | 2008-07-02 | Additional Folder
|  | Create a structure chart to show how pages link together and display the flow of the webpage. | 20 Minutes | 2008-07-02 | 2008-07-02 | Additional Folder |  | Use a logical folder structure and sensible folder and file names. The chart should also show links to the evidence that you want to include.
|  | The Eportfolio should include : a home page that includes: )who you are, your registration number and your centre name and number )the title of this SPB (Tell me a story Level 2) )the browser and resolution that should be used to view the eportfolio )links to the context pages. )context pages to introduce and link to required evidence. | - | - | - | - |  | *Make sure every File Format can be accessed by the Moderator, by looking at the Moderators toolkit.*
|  | Build the Eportfolio using the structure chart, make sure that there are links to every piece of evidence. Ensure that the Completed Story is clearly presented in one section. | 6 Lessons | 2008-07-02 | 2008-07-14 | Eportfolio - Website Section |  | Test the Eportfolio to ensure that it works on a stand alone computer. Ask for Etstusers opinions and make use of it. Make sure I have listed all the Browser types it has been viewed on. Check the size of the project, the maximum allowed is 30MB.
| Time for Test Users and Reviewers | Make use of Feedback from Test users about the Eportfolio, using it for the Project Review. | 30 Minutes | 2008-07-14 | 2008-07-14 | Project Log
Update my Project Plan and Log
12 | Review | Ask the teacher and some other users to make comments and evaluate the entire project, to be used in the Project Review. | 1 Lesson | 2008-07-16 | 2008-07-16 | Project Log
|  | Produce a Project review, using the notes to help, the mark alerts and project log. | 1 Lessons | 2008-07-16 | 2008-07-17 | Eportfolio |  | Include comments on what could be improved, making use of feedback from your teacher and other end-of-project reviewers. Convert your review to an acceptable format and save it for your eportfolio.